## HR_Onboarding
EmployeeID | Role | Department | StartDate | Manager | OnboardingTask | TaskOwner | DueDate | CompletedDate | Status | BlockedReason | TrainingModule | TrainingStatus | Notes | WeightedValue | CAC | ROAS | DaysLate
E2025-0001 | Recruiter | HR | 2025-02-10 | Grace Thompson | Complete Code of Conduct training | Employee | 2025-03-02 |  | Not started |  | Code of Conduct | Assigned | Not started |  |  |  | 322
E2025-0001 | Recruiter | HR | 2025-02-10 | Grace Thompson | Request core system access (HRIS/CRM/Jira) | Manager | 2025-02-25 |  | Not started |  | N/A | Not assigned | Not started |  |  |  | 327
E2025-0001 | Recruiter | HR | 2025-02-10 | Grace Thompson | Meet manager: 30-60-90 plan review | Manager | 2025-02-18 |  | Blocked | Waiting for laptop | N/A | Not assigned | Blocked: Waiting for laptop |  |  |  | 334
E2025-0001 | Recruiter | HR | 2025-02-10 | Grace Thompson | Set up email and Teams account | IT | 2025-02-16 |  | Blocked | Waiting for laptop | N/A | Not assigned | Blocked: Waiting for laptop |  |  |  | 336
E2025-0002 | HR Coordinator | HR | 2025-07-09 | Grace Thompson | Workstation/desk setup | Facilities | 2025-07-20 |  | Not started |  | N/A | Not assigned | Not started |  |  |  | 182
E2025-0002 | HR Coordinator | HR | 2025-07-09 | Grace Thompson | Request core system access (HRIS/CRM/Jira) | Manager | 2025-07-28 |  | In progress |  | N/A | Not assigned | In progress |  |  |  | 174
E2025-0002 | HR Coordinator | HR | 2025-07-09 | Grace Thompson | Set up multi-factor authentication (MFA) | IT | 2025-07-12 |  | Blocked | Waiting for laptop | N/A | Not assigned | Blocked: Waiting for laptop |  |  |  | 190
E2025-0002 | HR Coordinator | HR | 2025-07-09 | Grace Thompson | Meet manager: 30-60-90 plan review | Manager | 2025-07-17 |  | Done |  | N/A | Not assigned | Completed date missing (data issue) |  |  |  | 185
E2025-0003 | Software Engineer II | Engineering | 2025-11-10 | Ava Patel | Complete Code of Conduct training | Employee | 2025-11-23 | 2025-11-14 | Done |  | Code of Conduct | Completed |  |  |  |  | 0
E2025-0003 | Software Engineer II | Engineering | 2025-11-10 | Ava Patel | Badge & building access setup | Facilities | 2025-11-21 | 2025-11-16 | Done |  | N/A | Not assigned |  |  |  |  | 0
E2025-0003 | Software Engineer II | Engineering | 2025-11-10 | Ava Patel | Complete Data Privacy (GDPR) training | Employee | 2025-12-01 |  | In progress |  | Data Privacy (GDPR) | Assigned | In progress |  |  |  | 48
E2025-0003 | Software Engineer II | Engineering | 2025-11-10 | Ava Patel | Complete I-9 verification | HR | 2025-11-13 |  | In progress |  | N/A | Not assigned | In progress |  |  |  | 66
E2025-0004 | Office Coordinator | Operations | 2025-01-08 | Harper Wilson | Provision laptop and accessories | IT | 2025-01-09 | 2025-01-10 | Done |  | N/A | Not assigned | Device to be delivered to desk or shipped |  |  |  | 1
E2025-0004 | Office Coordinator | Operations | 2025-01-08 | Harper Wilson | Complete Code of Conduct training | Employee | 2025-01-14 | 2025-01-16 | Done |  | Code of Conduct | Completed |  |  |  |  | 2
E2025-0004 | Office Coordinator | Operations | 2025-01-08 | Harper Wilson | Submit direct deposit details | Employee | 2025-01-22 | 2025-01-09 | Done |  | N/A | Not assigned |  |  |  |  | 0
E2025-0004 | Office Coordinator | Operations | 2025-01-08 | Harper Wilson | Complete Security Awareness training | Employee | 2025-01-14 | 2025-01-11 | Done |  | Security Awareness | Completed |  |  |  |  | 0
E2025-0005 | FP&A Analyst | Finance | 2025-02-09 | Benjamin Lee | Complete Security Awareness training | Employee | 2025-02-15 |  | In progress |  | Security Awareness | Assigned | In progress |  |  |  | 337
E2025-0005 | FP&A Analyst | Finance | 2025-02-09 | Benjamin Lee | Enroll in benefits (medical/dental/401k) | HR | 2025-02-22 |  | In progress |  | N/A | Not assigned | In progress |  |  |  | 330
E2025-0005 | FP&A Analyst | Finance | 2025-02-09 | Benjamin Lee | Meet manager: 30-60-90 plan review | Manager | 2025-02-15 |  | In progress |  | N/A | Not assigned | In progress |  |  |  | 337
E2025-0005 | FP&A Analyst | Finance | 2025-02-09 | Benjamin Lee | Badge & building access setup | Facilities | 2025-02-20 |  | Not started |  | N/A | Not assigned | Not started |  |  |  | 332
E2025-0006 | Data Analyst | Engineering | 2025-09-05 | Sofia Ramirez | Team introductions / buddy assignment | Manager | 2025-09-12 | 2025-09-08 | Done |  | N/A | Not assigned |  |  |  |  | 0
E2025-0006 | Data Analyst | Engineering | 2025-09-05 | Sofia Ramirez | Request core system access (HRIS/CRM/Jira) | Manager | 2025-09-13 | 2025-09-11 | Done |  | N/A | Not assigned | Include required groups/roles in request |  |  |  | 0
E2025-0006 | Data Analyst | Engineering | 2025-09-05 | Sofia Ramirez | Provision laptop and accessories | IT | 2025-09-09 | 2025-09-11 | Done |  | N/A | Not assigned | Device to be delivered to desk or shipped |  |  |  | 2
E2025-0006 | Data Analyst | Engineering | 2025-09-05 | Sofia Ramirez | Read employee handbook and confirm | Employee | 2025-09-18 |  | In progress |  | Employee Handbook | Assigned | In progress |  |  |  | 122
E2025-0007 | Data Analyst | Engineering | 2025-09-24 | Ava Patel | Set up multi-factor authentication (MFA) | IT | 2025-09-29 |  | Blocked | Waiting for laptop | N/A | Not assigned | Blocked: Waiting for laptop |  |  |  | 111
E2025-0007 | Data Analyst | Engineering | 2025-09-24 | Ava Patel | Enroll in benefits (medical/dental/401k) | HR | 2025-10-05 | 2025-09-26 | Done |  | N/A | Not assigned |  |  |  |  | 0
E2025-0007 | Data Analyst | Engineering | 2025-09-24 | Ava Patel | Enroll in benefits (medical/dental/401k) | HR | 2025-10-05 | 2025-10-01 | Done |  | N/A | Not assigned | Duplicate task entry (data quality issue) |  |  |  | 0
E2025-0007 | Data Analyst | Engineering | 2025-09-24 | Ava Patel | Workstation/desk setup | Facilities | 2025-09-28 |  | Blocked | Manager unavailable | N/A | Not assigned | Blocked: Manager unavailable |  |  |  | 112
E2025-0008 | IT Support Technician | IT | 2025-01-22 | Jackson Moore | Provision laptop and accessories | IT | 2025-01-28 | 2025-01-27 | Done |  | N/A | Not assigned | Device to be delivered to desk or shipped |  |  |  | 0
E2025-0008 | IT Support Technician | IT | 2025-01-22 | Jackson Moore | Complete Workplace Harassment Prevention training | Employee | 2025-02-01 | 2025-01-30 | Done |  | Harassment Prevention | Completed |  |  |  |  | 0
E2025-0008 | IT Support Technician | IT | 2025-01-22 | Jackson Moore | Team introductions / buddy assignment | Manager | 2025-02-05 |  | In progress |  | N/A | Not assigned | In progress |  |  |  | 347
E2025-0008 | IT Support Technician | IT | 2025-01-22 | Jackson Moore | Workstation/desk setup | Facilities | 2025-01-26 | 2025-01-24 | Done |  | N/A | Not assigned |  |  |  |  | 0
E2025-0009 | QA Engineer | Engineering | 2025-02-10 | Sofia Ramirez | Complete expense policy acknowledgement | Finance | 2025-02-16 |  | Blocked | Manager unavailable | N/A | Not assigned | Blocked: Manager unavailable |  |  |  | 336
E2025-0009 | QA Engineer | Engineering | 2025-02-10 | Sofia Ramirez | Badge & building access setup | Facilities | 2025-02-20 |  | Done |  | N/A | Not assigned | Completed date missing (data issue) |  |  |  | 332
E2025-0009 | QA Engineer | Engineering | 2025-02-10 | Sofia Ramirez | Request core system access (HRIS/CRM/Jira) | Manager | 2025-02-16 | 2025-02-16 | Done |  | N/A | Not assigned | Include required groups/roles in request |  |  |  | 0
E2025-0009 | QA Engineer | Engineering | 2025-02-10 | Sofia Ramirez | Submit direct deposit details | Employee | 2025-02-15 |  | In progress |  | N/A | Not assigned | In progress |  |  |  | 337
E2025-0010 | Operations Associate | Operations | 2025-12-19 | Harper Wilson | Role tools walkthrough (apps & workflow) | Operations Lead | 2025-12-31 |  | Blocked | Access not granted | Role Tools 101 | Assigned | Blocked: Access not granted |  |  |  | 18
E2025-0010 | Operations Associate | Operations | 2025-12-19 | Harper Wilson | Request core system access (HRIS/CRM/Jira) | Manager | 2025-12-31 | 2025-12-30 | Done |  | N/A | Not assigned | Include required groups/roles in request |  |  |  | 0
E2025-0010 | Operations Associate | Operations | 2025-12-19 | Harper Wilson | Enroll in benefits (medical/dental/401k) | HR | 2025-12-24 |  | Done |  | N/A | Not assigned | Completed date missing (data issue) |  |  |  | 25
E2025-0010 | Operations Associate | Operations | 2025-12-19 | Harper Wilson | Enroll in benefits (medical/dental/401k) | HR | 2025-12-24 |  | Not started |  | N/A | Not assigned | Duplicate task entry (data quality issue); Not started |  |  |  | 25
E2025-0011 | Recruiter | HR | 2025-05-13 | Grace Thompson | Complete Code of Conduct training | Employee | 2025-05-31 |  | In progress |  | Code of Conduct | Assigned | In progress |  |  |  | 232
E2025-0011 | Recruiter | HR | 2025-05-13 | Grace Thompson | Complete I-9 verification | HR | 2025-05-23 |  | Not started |  | N/A | Not assigned | Not started |  |  |  | 240
E2025-0011 | Recruiter | HR | 2025-05-13 | Grace Thompson | Submit direct deposit details | Employee | 2025-05-26 |  | Blocked | Access not granted | N/A | Not assigned | Blocked: Access not granted |  |  |  | 237
E2025-0011 | Recruiter | HR | 2025-05-13 | Grace Thompson | Workstation/desk setup | Facilities | 2025-05-15 | 2025-05-17 | Done |  | N/A | Not assigned |  |  |  |  | 2
E2025-0012 | Customer Success Associate | Customer Support | 2025-05-12 | Chloe Davis | Complete Security Awareness training | Employee | 2025-05-26 | 2025-05-26 | Done |  | Security Awareness | Completed |  |  |  |  | 0
E2025-0012 | Customer Success Associate | Customer Support | 2025-05-12 | Chloe Davis | Submit direct deposit details | Employee | 2025-05-29 |  | Blocked | Manager unavailable | N/A | Not assigned | Duplicate task entry (data quality issue); Blocked: Manager unavailable |  |  |  | 234
E2025-0012 | Customer Success Associate | Customer Support | 2025-05-12 | Chloe Davis | Submit direct deposit details | Employee | 2025-05-29 | 2025-05-16 | Done |  | N/A | Not assigned |  |  |  |  | 0
E2025-0012 | Customer Success Associate | Customer Support | 2025-05-12 | Chloe Davis | Set up multi-factor authentication (MFA) | IT | 2025-05-15 |  | Done |  | N/A | Not assigned | Completed date missing (data issue) |  |  |  | 248
E2025-0013 | Sales Operations Analyst | Sales | 2025-01-12 | Ethan Brooks | Enroll in benefits (medical/dental/401k) | HR | 2025-01-26 | 2025-01-22 | Done |  | N/A | Not assigned |  |  |  |  | 0
E2025-0013 | Sales Operations Analyst | Sales | 2025-01-12 | Ethan Brooks | Workstation/desk setup | Facilities | 2025-01-21 | 2025-01-13 | Done |  | N/A | Not assigned |  |  |  |  | 0
E2025-0013 | Sales Operations Analyst | Sales | 2025-01-12 | Ethan Brooks | Submit direct deposit details | Employee | 2025-01-29 | 2025-01-14 | Done |  | N/A | Not assigned |  |  |  |  | 0
E2025-0013 | Sales Operations Analyst | Sales | 2025-01-12 | Ethan Brooks | Request core system access (HRIS/CRM/Jira) | Manager | 2025-01-29 | 2025-01-21 | Done |  | N/A | Not assigned | Include required groups/roles in request |  |  |  | 0
E2025-0014 | Technical Support Specialist | Customer Support | 2025-01-18 | Chloe Davis | Team introductions / buddy assignment | Manager | 2025-02-06 |  | Done |  | N/A | Not assigned | Completed date missing (data issue) |  |  |  | 346
E2025-0014 | Technical Support Specialist | Customer Support | 2025-01-18 | Chloe Davis | Workstation/desk setup | Facilities | 2025-01-22 |  | In progress |  | N/A | Not assigned | In progress |  |  |  | 361
E2025-0014 | Technical Support Specialist | Customer Support | 2025-01-18 | Chloe Davis | Badge & building access setup | Facilities | 2025-01-28 | 2025-01-27 | Done |  | N/A | Not assigned |  |  |  |  | 0
E2025-0014 | Technical Support Specialist | Customer Support | 2025-01-18 | Chloe Davis | Provision laptop and accessories | IT | 2025-01-22 | 2025-01-19 | Done |  | N/A | Not assigned | Device to be delivered to desk or shipped |  |  |  | 0
E2025-0015 | Technical Support Specialist | Customer Support | 2025-09-15 | Daniel Nguyen | Role tools walkthrough (apps & workflow) | Support Lead | 2025-09-29 | 2025-09-30 | Done |  | Role Tools 101 | Completed |  |  |  |  | 1
E2025-0015 | Technical Support Specialist | Customer Support | 2025-09-15 | Daniel Nguyen | Complete expense policy acknowledgement | Finance | 2025-09-21 | 2025-09-20 | Done |  | N/A | Not assigned |  |  |  |  | 0
E2025-0015 | Technical Support Specialist | Customer Support | 2025-09-15 | Daniel Nguyen | Complete Security Awareness training | Employee | 2025-09-23 | 2025-09-20 | Done |  | Security Awareness | Completed |  |  |  |  | 0
E2025-0015 | Technical Support Specialist | Customer Support | 2025-09-15 | Daniel Nguyen | Set up multi-factor authentication (MFA) | IT | 2025-09-22 | 2025-09-22 | Done |  | N/A | Not assigned |  |  |  |  | 0
E2025-0016 | People Operations Specialist | HR | 2025-08-06 | Grace Thompson | Complete Security Awareness training | Employee | 2025-08-25 | 2025-08-10 | Done |  | Security Awareness | Completed |  |  |  |  | 0
E2025-0016 | People Operations Specialist | HR | 2025-08-06 | Grace Thompson | Complete I-9 verification | HR | 2025-08-10 |  | Done |  | N/A | Not assigned | Completed date missing (data issue) |  |  |  | 161
E2025-0016 | People Operations Specialist | HR | 2025-08-06 | Grace Thompson | Workstation/desk setup | Facilities | 2025-08-12 |  | In progress |  | N/A | Not assigned | In progress |  |  |  | 159
E2025-0016 | People Operations Specialist | HR | 2025-08-06 | Grace Thompson | Meet manager: 30-60-90 plan review | Manager | 2025-08-25 | 2025-08-08 | Done |  | N/A | Not assigned | Schedule on calendar during first week |  |  |  | 0
E2025-0017 | Systems Administrator | IT | 2025-09-21 | Jackson Moore | Read employee handbook and confirm | Employee | 2025-10-01 |  | In progress |  | Employee Handbook | Assigned | In progress |  |  |  | 109
E2025-0017 | Systems Administrator | IT | 2025-09-21 | Jackson Moore | Role tools walkthrough (apps & workflow) | Operations Lead | 2025-10-12 | 2025-10-10 | Done |  | Role Tools 101 | Completed |  |  |  |  | 0
E2025-0017 | Systems Administrator | IT | 2025-09-21 | Jackson Moore | Workstation/desk setup | Facilities | 2025-09-28 |  | In progress |  | N/A | Not assigned | In progress |  |  |  | 112
E2025-0017 | Systems Administrator | IT | 2025-09-21 | Jackson Moore | Request core system access (HRIS/CRM/Jira) | Manager | 2025-09-26 | 2025-09-28 | Done |  | N/A | Not assigned | Include required groups/roles in request |  |  |  | 2
E2025-0018 | Growth Analyst | Marketing | 2025-03-19 | Lucas Wright | Complete I-9 verification | HR | 2025-03-31 |  | Not started |  | N/A | Not assigned | Not started |  |  |  | 293
E2025-0018 | Growth Analyst | Marketing | 2025-03-19 | Lucas Wright | Enroll in benefits (medical/dental/401k) | HR | 2025-04-02 | 2025-03-25 | Done |  | N/A | Not assigned |  |  |  |  | 0
E2025-0018 | Growth Analyst | Marketing | 2025-03-19 | Lucas Wright | Request core system access (HRIS/CRM/Jira) | Manager | 2025-04-01 |  | In progress |  | N/A | Not assigned | In progress |  |  |  | 292
E2025-0018 | Growth Analyst | Marketing | 2025-03-19 | Lucas Wright | Complete Workplace Harassment Prevention training | Employee | 2025-03-27 |  | Blocked | Waiting for laptop | Harassment Prevention | Assigned | Blocked: Waiting for laptop |  |  |  | 297
E2025-0019 | Systems Administrator | IT | 2025-03-06 | Jackson Moore | Enroll in benefits (medical/dental/401k) | HR | 2025-03-11 |  | In progress |  | N/A | Not assigned | In progress |  |  |  | 313
E2025-0019 | Systems Administrator | IT | 2025-03-06 | Jackson Moore | Badge & building access setup | Facilities | 2025-03-18 | 2025-03-12 | Done |  | N/A | Not assigned |  |  |  |  | 0
E2025-0019 | Systems Administrator | IT | 2025-03-06 | Jackson Moore | Submit direct deposit details | Employee | 2025-03-12 |  | Not started |  | N/A | Not assigned | Not started |  |  |  | 312
E2025-0019 | Systems Administrator | IT | 2025-03-06 | Jackson Moore | Workstation/desk setup | Facilities | 2025-03-13 | 2025-03-08 | Done |  | N/A | Not assigned |  |  |  |  | 0
E2025-0020 | Office Coordinator | Operations | 2025-08-19 | Harper Wilson | Request core system access (HRIS/CRM/Jira) | Manager | 2025-08-27 |  | In progress |  | N/A | Not assigned | In progress |  |  |  | 144
E2025-0020 | Office Coordinator | Operations | 2025-08-19 | Harper Wilson | Set up email and Teams account | IT | 2025-08-25 |  | In progress |  | N/A | Not assigned | Duplicate task entry (data quality issue); In progress |  |  |  | 146
E2025-0020 | Office Coordinator | Operations | 2025-08-19 | Harper Wilson | Set up email and Teams account | IT | 2025-08-25 |  | Not started |  | N/A | Not assigned | Not started |  |  |  | 146
E2025-0020 | Office Coordinator | Operations | 2025-08-19 | Harper Wilson | Read employee handbook and confirm | Employee | 2025-08-29 | 2025-08-22 | Done |  | Employee Handbook | Completed |  |  |  |  | 0
E2025-0021 | People Operations Specialist | HR | 2025-06-19 | Grace Thompson | Workstation/desk setup | Facilities | 2025-06-29 | 2025-06-23 | Done |  | N/A | Not assigned |  |  |  |  | 0
E2025-0021 | People Operations Specialist | HR | 2025-06-19 | Grace Thompson | Complete Code of Conduct training | Employee | 2025-06-26 | 2025-06-26 | Done |  | Code of Conduct | Completed |  |  |  |  | 0
E2025-0021 | People Operations Specialist | HR | 2025-06-19 | Grace Thompson | Read employee handbook and confirm | Employee | 2025-07-04 | 2025-06-28 | Done |  | Employee Handbook | Completed |  |  |  |  | 0
E2025-0021 | People Operations Specialist | HR | 2025-06-19 | Grace Thompson | Role tools walkthrough (apps & workflow) | Operations Lead | 2025-07-09 |  | In progress |  | Role Tools 101 | Assigned | In progress |  |  |  | 193
E2025-0022 | Content Strategist | Marketing | 2025-11-11 | Olivia Martin | Team introductions / buddy assignment | Manager | 2025-11-25 | 2025-11-20 | Done |  | N/A | Not assigned |  |  |  |  | 0
E2025-0022 | Content Strategist | Marketing | 2025-11-11 | Olivia Martin | Workstation/desk setup | Facilities | 2025-11-13 | 2025-11-12 | Done |  | N/A | Not assigned | Duplicate task entry (data quality issue) |  |  |  | 0
E2025-0022 | Content Strategist | Marketing | 2025-11-11 | Olivia Martin | Complete expense policy acknowledgement | Finance | 2025-11-29 |  | Not started |  | N/A | Not assigned | Not started |  |  |  | 50
E2025-0022 | Content Strategist | Marketing | 2025-11-11 | Olivia Martin | Workstation/desk setup | Facilities | 2025-11-13 | 2025-11-14 | Done |  | N/A | Not assigned |  |  |  |  | 1
E2025-0023 | Data Analyst | Engineering | 2025-10-10 | Ava Patel | Role tools walkthrough (apps & workflow) | Engineering Enablement | 2025-10-23 | 2025-10-24 | Done |  | Role Tools 101 | Completed |  |  |  |  | 1
E2025-0023 | Data Analyst | Engineering | 2025-10-10 | Ava Patel | Complete expense policy acknowledgement | Finance | 2025-10-25 |  | Not started |  | N/A | Not assigned | Not started |  |  |  | 85
E2025-0023 | Data Analyst | Engineering | 2025-10-10 | Ava Patel | Request core system access (HRIS/CRM/Jira) | Manager | 2025-10-22 | 2025-10-16 | Done |  | N/A | Not assigned | Include required groups/roles in request |  |  |  | 0
E2025-0023 | Data Analyst | Engineering | 2025-10-10 | Ava Patel | Workstation/desk setup | Facilities | 2025-10-20 | 2025-10-13 | Done |  | N/A | Not assigned |  |  |  |  | 0
E2025-0024 | IT Analyst | IT | 2025-12-13 | Jackson Moore | Set up multi-factor authentication (MFA) | IT | 2025-12-15 |  | In progress |  | N/A | Not assigned | In progress |  |  |  | 34
E2025-0024 | IT Analyst | IT | 2025-12-13 | Jackson Moore | Complete I-9 verification | HR | 2025-12-24 |  | In progress |  | N/A | Not assigned | In progress |  |  |  | 25
E2025-0024 | IT Analyst | IT | 2025-12-13 | Jackson Moore | Team introductions / buddy assignment | Manager | 2025-12-22 | 2025-12-20 | Done |  | N/A | Not assigned |  |  |  |  | 0
E2025-0024 | IT Analyst | IT | 2025-12-13 | Jackson Moore | Complete Security Awareness training | Employee | 2025-12-22 | 2025-12-14 | Done |  | Security Awareness | Completed |  |  |  |  | 0
E2025-0025 | Operations Associate | Operations | 2025-04-03 | Harper Wilson | Complete Security Awareness training | Employee | 2025-04-17 | 2025-04-17 | Done |  | Security Awareness | Completed |  |  |  |  | 0
E2025-0025 | Operations Associate | Operations | 2025-04-03 | Harper Wilson | Set up multi-factor authentication (MFA) | IT | 2025-04-12 |  | Not started |  | N/A | Not assigned | Not started |  |  |  | 281
E2025-0025 | Operations Associate | Operations | 2025-04-03 | Harper Wilson | Complete Workplace Harassment Prevention training | Employee | 2025-04-20 |  | Done |  | Harassment Prevention | Completed | Completed date missing (data issue) |  |  |  | 273
E2025-0025 | Operations Associate | Operations | 2025-04-03 | Harper Wilson | Enroll in benefits (medical/dental/401k) | HR | 2025-04-17 |  | In progress |  | N/A | Not assigned | In progress |  |  |  | 276
E2025-0026 | Operations Associate | Operations | 2025-11-25 | Harper Wilson | Complete expense policy acknowledgement | Finance | 2025-12-08 | 2025-11-29 | Done |  | N/A | Not assigned |  |  |  |  | 0
E2025-0026 | Operations Associate | Operations | 2025-11-25 | Harper Wilson | Complete Security Awareness training | Employee | 2025-12-04 | 2025-11-29 | Done |  | Security Awareness | Completed |  |  |  |  | 0
E2025-0026 | Operations Associate | Operations | 2025-11-25 | Harper Wilson | Complete Data Privacy (GDPR) training | Employee | 2025-12-06 | 2025-12-08 | Done |  | Data Privacy (GDPR) | Completed |  |  |  |  | 2
E2025-0026 | Operations Associate | Operations | 2025-11-25 | Harper Wilson | Provision laptop and accessories | IT | 2025-11-30 | 2025-11-26 | Done |  | N/A | Not assigned | Device to be delivered to desk or shipped |  |  |  | 0
E2025-0027 | Sales Operations Analyst | Sales | 2025-12-05 | Ethan Brooks | Complete Data Privacy (GDPR) training | Employee | 2025-12-13 |  | Blocked | Access not granted | Data Privacy (GDPR) | Assigned | Blocked: Access not granted |  |  |  | 36
E2025-0027 | Sales Operations Analyst | Sales | 2025-12-05 | Ethan Brooks | Submit direct deposit details | Employee | 2025-12-15 | 2025-12-14 | Done |  | N/A | Not assigned |  |  |  |  | 0
E2025-0027 | Sales Operations Analyst | Sales | 2025-12-05 | Ethan Brooks | Complete I-9 verification | HR | 2025-12-10 |  | Blocked | Access not granted | N/A | Not assigned | Blocked: Access not granted |  |  |  | 39
E2025-0027 | Sales Operations Analyst | Sales | 2025-12-05 | Ethan Brooks | Enroll in benefits (medical/dental/401k) | HR | 2025-12-13 | 2025-12-10 | Done |  | N/A | Not assigned |  |  |  |  | 0
E2025-0028 | Accounts Payable Specialist | Finance | 2025-04-12 | Benjamin Lee | Enroll in benefits (medical/dental/401k) | HR | 2025-04-24 | 2025-04-23 | Done |  | N/A | Not assigned |  |  |  |  | 0
E2025-0028 | Accounts Payable Specialist | Finance | 2025-04-12 | Benjamin Lee | Role tools walkthrough (apps & workflow) | Operations Lead | 2025-04-18 | 2025-04-20 | Done |  | Role Tools 101 | Completed |  |  |  |  | 2
E2025-0028 | Accounts Payable Specialist | Finance | 2025-04-12 | Benjamin Lee | Complete Data Privacy (GDPR) training | Employee | 2025-04-23 |  | Not started |  | Data Privacy (GDPR) | Assigned | Not started |  |  |  | 270
E2025-0028 | Accounts Payable Specialist | Finance | 2025-04-12 | Benjamin Lee | Workstation/desk setup | Facilities | 2025-04-20 | 2025-04-18 | Done |  | N/A | Not assigned |  |  |  |  | 0
E2025-0029 | Data Analyst | Engineering | 2025-10-09 | Noah Kim | Set up email and Teams account | IT | 2025-10-13 |  | In progress |  | N/A | Not assigned | In progress |  |  |  | 97
E2025-0029 | Data Analyst | Engineering | 2025-10-09 | Noah Kim | Set up multi-factor authentication (MFA) | IT | 2025-10-15 |  | Done |  | N/A | Not assigned | Completed date missing (data issue) |  |  |  | 95
E2025-0029 | Data Analyst | Engineering | 2025-10-09 | Noah Kim | Badge & building access setup | Facilities | 2025-10-16 |  | In progress |  | N/A | Not assigned | In progress |  |  |  | 94
E2025-0029 | Data Analyst | Engineering | 2025-10-09 | Noah Kim | Complete Workplace Harassment Prevention training | Employee | 2025-10-24 | 2025-10-20 | Done |  | Harassment Prevention | Completed |  |  |  |  | 0
E2025-0030 | IT Support Technician | IT | 2025-05-18 | Jackson Moore | Complete expense policy acknowledgement | Finance | 2025-05-28 | 2025-05-26 | Done |  | N/A | Not assigned |  |  |  |  | 0
E2025-0030 | IT Support Technician | IT | 2025-05-18 | Jackson Moore | Workstation/desk setup | Facilities | 2025-05-25 | 2025-05-27 | Done |  | N/A | Not assigned | Duplicate task entry (data quality issue) |  |  |  | 2
E2025-0030 | IT Support Technician | IT | 2025-05-18 | Jackson Moore | Read employee handbook and confirm | Employee | 2025-05-24 |  | In progress |  | Employee Handbook | Assigned | In progress |  |  |  | 239
E2025-0030 | IT Support Technician | IT | 2025-05-18 | Jackson Moore | Workstation/desk setup | Facilities | 2025-05-25 | 2025-05-24 | Done |  | N/A | Not assigned |  |  |  |  | 0
Formulas:
DaysLate = IF(HRTable[[#This Row],[DueDate]]="", "", MAX(0, IF(HRTable[[#This Row],[CompletedDate]]="", TODAY()-HRTable[[#This Row],[DueDate]], HRTable[[#This Row],[CompletedDate]]-HRTable[[#This Row],[DueDate]])))